## 22-23
SISKIYOU COUNTY SB-1 2022/23
ROAD MAINTENANCE AND REHABILITAION (RMRA) PROJECT LIST
[10 empty] | 2022/23 RMRA - | 5032384
Work | Road | Project |  |  | Road | Est. Useful | Mile Post | Mile Post |  |  | Completion | CAMS Project Number
Order Num | Dist. | Title | Project Description | Road Name / Location | Number | Life (Years) | Begin | End | Length | Estimate | Date Est.
SB-1 Routine Maintenance Project List
| All | Roadway Striping and Pavement Markings | This routine maintenance item includes restriping Centerline, edge line and reapplying painted and thermoplastic legends stop bars and crosswalks throughout Siskiyou County. | Work will be on roads that currently have existing paint or thermoplastic pavement markings. Areas include Yreka, Montague, Scott Valley, Happy Camp, Butte Valley Gazelle, Mt Shasta, McCloud, Dunsmuir, and Tulelake. |  | 1-2 | N/A | N/A |  | 250000 | 2023-06-30 | 2103-RD 1920 STRIP
| All | Sign upgrade and Maintenance | This project includes upgrading of Regulatory signs to meet the Retroreflecivity requirement. Project will also include maintenance of road side delineation and post repair. | Location will be determined by priority based on routine Retroreflecivity Study. Locations subject to change based upon needs and available resources throughout the year. |  | 5-7 | N/A | N/A |  | 120000 | 2023-06-30 | 2103-RD 2021 SIGNS
| All | Roadside Tree Trimming and Vegetation Management | This project consists of hazard tree removal, tree trimming, mowing and road side grass and weed control. Countywide. | Various location throughout Siskiyou County based on need. Planed areas include Klamath River Rd, McCloud area and the Mt Shasta area, Yreka and Montague area, Scott Valley area. |  | 1-2 | N/A | N/A |  | 500000 | 2023-06-30 | 2103-RD 2021 VEG MGT
| All | Gravel Road Maintenance | This routine maintenance item includes gravel grading and surface application of crushed rock. | Roads include but are not limited to: Louie Road, Old State Hwy, Sheepy Creek Road, Doris Brownell Road, Willow Creek Red Rock Road, Big Springs Road, York Road, Willow Creek Road, Crushed rock application will be prioritized by need. |  | 1-5 | N/A | N/A |  | 800000 | 2023-06-30 | 2103-RD 2021 GRVL RDS
| All | Aggregate Production/Purchase | This project will consist of production of aggregate materials at the County's Yellow Butte and aggregate purchases for Districts 4,5 and 6. | Yellow Butte cinder production and other aggregate purchases |  | 1-3 | N/A | N/A |  | 223687 | 2023-06-30 | 2103-RD 2021 AGG PROD
| All | Maintenance/Rehabilitation of existing unpaved shoulder | This routine maintenance item will consist of re-profiling, grading and adding aggregate base material were needed. | Shoulder improvements will be prioritized by current condition. Areas include Montague, Yreka, Gazelle, Scott Valley, Butte Valley, Tulelake, McCloud, Dunsmuir, and Mt Shasta. |  | 1-2 | N/A | N/A |  | 300000 | 2023-06-30 | 2103-RD 2021 SHOULDER
| All | Culvert and Ditch Maintenance | This project will consist of debris removal from drainages, ditches and culverts, reestablishing ditch lines. In an effort to maintain flow lines and reduce the potential for flooding and sediment disbursement into waterways. | Various location throughout Siskiyou County based on need. Planned areas include Mt Shasta, Montague,Gazelle,Scott valley area, Butte valley area and the Happy Camp area. |  | 1-3 | N/A | N/A |  | 500000 | 2023-06-30 | 2103-RD 2021 DITCH
| All | Pavement patching | Project consists of pothole repair, thin asphalt overlay, crack fill and sealing, with the intent of repairing unsafe, damaged or failing roadway. | Priority will be dictated by need and roadway safety. Planned areas include Mt Shasta, Scott Valley, Happy Camp, Forks of the Salmon, Butte Valley, Tulelake, Gazelle, McCloud, Dunsmuir, Montague, and Yreka areas. |  | 1-5 | N/A | N/A |  | 310000 | 2023-06-30
| All | Maintenance of Public Works Equipment. | Project consists of repair and servicing of Public Works equipment. | Work will be primarily completed at the Road Dept. shops located in Yreka, Dorris, Fort Jones, Etna, Happy Camp, Mt Shasta, and Gazelle. | [5 empty] | 650000
[7 empty] | Routine Maintenance Total |  |  | 3653687
[7 empty] | 20/21 RMRA Allocation |  |  | 4192019
[7 empty] | Total left for Rehab Projects |  |  | 538332
[7 empty] | Per District Project Allocation |  |  | 89722
SB-1 Preventative Maintenance Project List
| 1 | Chip Seal District 1 | Project consists of asphalt repair with follow-up 3/8" chip seal. | Airport Road | 7K02 | 5-7 | MP 0 | MP 3 | 3 | 229476 | 2023-09-30 | 2103-RD RMRA2021 A
| 2 | Chip Seal District 2 | Project consists of asphalt repair with follow-up 3/8" chip seal. | Madison Drive, Monroe Way, Shasta Acres, Shasta Way,Lotus Lane Alpine Drive. | 2M095, 2M098, 2M039, 2M082, 2M041, 2M083, | 5-7 | MP 0 | MP 0.52, 0.63, 0.57, 0.64, 0.23, 0.31, | 2.9 | 237510 | 2023-09-30 | 2103-RD RMRA2021 C
| 3 | Chip Seal District 3 | Project consists of asphalt repair with follow-up 3/8" chip seal. | South Phillipe Lane, Old Westside Road. | 7J05, 5K006 | 5-7 | MP 4.24,0, | MP 7.4, 1.25 | 4.25 | 235292 | 2023-09-30 | 2103-RD RMRA2021 D
| 4 | Chip Seal District 4 | Project consists of asphalt repair with follow-up 3/8" chip seal. | West Moffett Creek Road | 6H001 | 5-7 | MP 0,0 | MP 3.6 | 3.6 | 231202 | 2023-09-30 | 2103-RD RMRA2021 E
| 5 | Chip Seal District 5 | Project consists of asphalt repair with follow-up 3/8" chip seal. | Eastside Road | 4G05A | 5-7 | MP 0,0 | MP 4.5 | 4.5 | 209502 | 2023-09-30 | 2103-RD RMRA2021 F
| 6 | Chip Seal District 6 | Project consists of asphalt repair with follow-up 3/8" chip seal. | East Butte Valley Road | 9R002 | 5-7 | MP 0 | MP 4 | 4 | 235715 | 2023-09-30 | 2103-RD RMRA2021 G
[7 empty] | Rehab Project Total |  |  | 1378697
[7 empty] | SB-1 RMRA PROJECT ESTIMATE TOTAL |  |  |  | 5032384 | -840365
0
Note on D16: Todd Lamanna: Including Autoserver Costs of 40K