## ReadMe
Applicants must complete all worksheets unless otherwise noted.
Project Budget (Worksheets 1A and 1B)
The Project Budget worksheet must clearly depict how grant funds will be spent. Costs should be reasonable in proportion to the proposed deliverables and Scope of Work. Specify the number of salaried employees and contractors funded under the grant and the cost basis for each. The budget must identify any income received from the sale of forest products or other income generated as a result of the project and how those funds will be reinvested in the project. CAL FIRE reserves the right to fund only a portion of the proposed budget items. Up to 12% of the total direct costs, excluding equipment costs, is allowable as indirect costs. See Grant Guidelines for a complete listing of elibilble costs. Research Program applicants seeking funding over two phases should submit separate budgets for Phase 1 in worksheet 1A, and Phase 2 in worksheet 1B. Worksheet 1B (Phase 2 Budget) is not required from Forest Health and Forest Legacy applicants.)
Treatment Areas (Worksheet 2)
The Treatment Areas worksheet must specify the treatment areas, ownership type, and funds to be spent by treatment. List only one ownership type, treatment objective, and treatment activity per row. All treatment areas must be included and a treatment area may need to be listed more than once. Add more rows if needed. Input options are provided in dropdown menus and reference tables for ownership type, treatment objective, treatment activity, and CEQA/NEPA status. Required for all Forest Health applicants and all other applicants with field treatments planned for grant funds.
Work Plan (Worksheet 3)
Complete the Work Plan worksheet with appropriate detail describing the phases of work necessary to successfully implement the project. List the major phases of work by quarter for each project or treatment area included in the application. Ensure that all phases of work will be completed before the end of the project performance period. Required for all applicants.
Environmental Compliance (Worksheet 4)
List all the treatment areas and treatments proposed to be funded under the grant in the Environmental Compliance worksheet. Identify the environmental compliance document that have been "completed and filed" or "not completed and filed." The documents that have been completed and filed should be submitted with the grant application. All environmental permitting must be completed within one year of the grant agreement start date. Required for all Forest Health applicants. If there are no CEQA requirements, please state that and explain why no documents or processes are needed. Research Program applicants need not complete unless treatments are proposed using grant funds.)

## 1A. Project Budget
CAL FIRE Tracking # 20-FH-SKU-010 Project Title: McKinley Scott Fuel Reduction |  | CAL FIRE Forest Health Program California Climate Investments (Required from all aplicants. For Research Program applicants with two-phase projects, use this sheet for Phase 1 budget only.) |  |  |  | Siskiyou County
Worksheet 1A: Grant Info
Budget Item | Description | Units (if applicable) | Rate (if applicable) | CAL FIRE Grant Share | Program Income | Grantee Match | Total
A. Salaries and Wages (Job title/Classification/Role) |  | (# hours) | ($/hour) | 36200 | 0 | 0 | 36200
Siskiyou County Staff | Manage grant submissions and payments | 994 | $36.40/hour | 36200 |  |  | 36200
0
0
0
B. Employee Benefits (Job title/Classification/Role) |  | (# hours) | ($/hour) | 23800 | 0 | 0 | 23800
Siskiyou County Staff | Manage grant submissions and payments | 994 | $23.97/hour | 23800 |  |  | 23800
0
0
0
C. Contractual (Role in project) |  | (e.g., # hours, # acres, # BDT) | (e.g., $/hour, $/acre, $/BDT) | 4817427 | 75375 | 843370 | 5736172
RPF - FWS | Prepare CEQA documents; supervise contractors & company staff as appropriate; produce invoices, quarterly reports, and grant closeout report for AKF owned timberlands | 2000 | $90/hr | 0 | 0 | 180000 | 180000
Forestry technician FWS | Field Layout on AKF owned timberlands | 240 | $60/hr | 0 | 0 | 14400 | 14400
Biologist | Sensitive species surveys and reports | 150 hours | $75/hr | 0 | 0 | 11250 | 11250
Biology technician (2) | Species surveys | 300 hours | $60/hr | 0 | 0 | 18000 | 18000
FGS Heavy Equipment Operator | Operates FGS masticator on AKF owned timberlands | 500 hours | 86.99 | 0 | 0 | 43495 | 43495
FGS Heavy Equipment Assistant | Operate service truck, fire watch on AKF owned timberlands | 500 hours | 76.56 | 0 | 0 | 38280 | 38280
Reforestation Forester FWS | Supervise herbicide contractor on AKF owned timberlands | 80 hours | $90/hr | 0 | 0 | 14400 | 14400
Mastication | 2 to 3 contractors/year will be hired to masticate brush, dead trees, and small green trees. Anticipated employment is 5-9 personnel. | 957 | $1600/ac | 1531200 |  |  | 1531200
Herbicide application | 1 contractor will be hired to hand spray the selected brush stands. Anticipated employment is 6 personnel. | 830 | $150/acre | 124500 |  |  | 124500
Pre-commercial thinning | 1 to 2 contractors/year will be hired to cut brush, dead trees and small green trees. Anticipated employment is 6-15 personnel. | 408 | $950/acre | 387600 |  |  | 387600
Pruning | Pruning leave trees up to 8 feet, and treating associated slash. | 514 | $95/acre | 48830 |  |  | 48830
Rx burn assistance | Hire a contractor to assist in burn preparation activities and implementation of Rx burn (KNF will provide all resources to burn additional 800 acres) | 250 | $600/acre | 150000 |  | 400000 | 550000
Thinning-Chipping with partial biomass removal | 1 to 2 contractors/year will be hired to chip smaller downed material from thinning. Anticipated employment is 6-12 personnel. | 754 | $2150/acre | 1658800 | 75375 |  | 1734175
Lowbed | Transport excavator as necessary | 10 Haul trips in/ 10 trips out | $160/hour | 23040 |  |  | 23040
Shasta Valley RCD | Project management including Lead Agency for CEQA, report writing, contracts, inspection, invoicing, and monitoring |  | $56,650/year | 169950
FGS Excavator operation on AKF owned timberlands |  | 40 | $898.80day |  |  | 35952 | 35952
Project Manager |  | 10,000 miles | $0.56/mile | 5600 |  |  | 5600
RPF - FWS |  | 12,000 miles | $0.56/mile |  |  | 6720 | 6720
RPF - MCTC |  | 12,000 miles | $0.56/mile |  |  | 6720 | 6720
Forestry technicians FWS |  | 6,000 miles | $0.56/mile |  |  | 3360 | 3360
Forestry technicians MCTC |  | 6,000 miles | $0.56/mile |  |  | 3360 | 3360
Biologist |  | 5,000 miles | $0.56/mile |  |  | 2800 | 2800
Biology technicians |  | 10,000 miles | $0.56/mile |  |  | 5600 | 5600
Heavy Equipment Operator & Assistant |  | 6,000 miles | $0.56/mile |  |  | 3360 | 3360
Reforestation Forester FWS |  | 1,500 miles | $0.56/mile |  |  | 840 | 840
Reforestation Forester MCTC |  | 1,500 miles | $0.56/mile |  |  | 840 | 840
Boundary Flagging |  | 720 rolls | $1.75/roll |  |  | 1260 | 1260
Watercourse & STZ Flagging |  | 60 rolls | $2.50/roll |  |  | 150 | 150
Sample Marking Paint |  | 100 cans | $4.65/can |  |  | 465 | 465
CEQA filing fees |  | 15 Documents | $64/document | 965 |  |  | 965
Wildlife Monitoring | Monitoring of impacts on sensitive species (i.e. fisher) |  |  | 416942 |  | 52118 | 469060
Effectiveness Monitoring | Monitoring effectiveness of fuel treatments regarding vertical and horizontal spacing of residual fuel components |  |  | 300000 |  |  | 300000
0
D. Travel |  | (e.g., # miles) | (e.g., $/miles) | 0 | 0 | 0 | 0
0
E. Supplies |  |  |  | 0 | 0 | 0 | 0
F. Equipment |  |  |  | 0 | 0 | 0 | 0
0
G. Other |  |  |  | 0 | 0 | 0 | 0
0
TOTAL DIRECT COSTS |  |  |  | 4877427 | 75375 | 843370 | 5796172
INDIRECT COSTS |  | (12% max for CAL FIRE Grant Share and Program Income, excluding equipment) |  | 120000 |  |  | 120000
County Administrative costs |  |  | $40,000/year | 120000
TOTAL GRANT PROPOSED COSTS |  |  |  | 4997427 | 75375 | 843370 | 5840797

## 1B. Project Budget (Phase 2)
CAL FIRE Tracking # (as assigned) Project Title |  | CAL FIRE Forest Health Program California Climate Investments (Required only from Research Program applicants seeking funding over two phases. Forest Health and Legacy applicants need not complete.) |  |  |  | Organization
Worksheet 1B: Grant Info Phase 2
Budget Item | Description | Units (if applicable) | Rate (if applicable) | CAL FIRE Grant Share | Program Income | Grantee Match | Total
A. Salaries and Wages (Job title/Classification/Role) |  | (# hours) | ($/hour) | 0 | 0 | 0 | 0
0
0
0
0
B. Employee Benefits (Job title/Classification/Role) |  | (# hours) | ($/hour) | 0 | 0 | 0 | 0
0
0
0
0
C. Contractual (Role in project) |  | (e.g., # hours, # acres, # BDT) | (e.g., $/hour, $/acre, $/BDT) | 0 | 0 | 0 | 0
0
0
0
0
D. Travel |  | (e.g., # miles) | (e.g., $/miles) | 0 | 0 | 0 | 0
0
0
0
0
E. Supplies |  |  |  | 0 | 0 | 0 | 0
0
0
0
0
F. Equipment |  |  |  | 0 | 0 | 0 | 0
0
0
0
0
G. Other |  |  |  | 0 | 0 | 0 | 0
0
0
0
0
TOTAL DIRECT COSTS |  |  |  | 0 | 0 | 0 | 0
INDIRECT COSTS |  | (12% max for CAL FIRE Grant Share and Program Income, excluding equipment) |  | 0 |  |  | 0
TOTAL GRANT PROPOSED COSTS |  |  |  | 0 | 0 | 0 | 0

## 2. Treatment Areas
CAL FIRE Tracking # 20-FH-SKU-010 Project Title: McKinley Scott Fuel Reduction |  |  |  | CAL FIRE Forest Health Program California Climate Investments (Forest Health: Required for all applicants. Research and Forest Legacy: Complete this worksheet only if field treatments will be implemented using grant funds.) |  |  | Siskiyou County
Worksheet 2: Treatment Areas
Applicant:
Application ID:
List only one ownership type and only one treatment type per row. You may need to list each area more than once.
Add more rows if needed. All treatment areas must be included.
See Reference Tables for input options -->
TreatmentNumber | TreatmentArea | OwnershipType | Acreage | Treatment Objective | Treatment Activity | StatusNEPA | StatusCEQA | LeadAgency | GrantFunds | MatchingFunds
1.1 | Scott Bar Ridge 1 | Private (industrial forestry) | 119 | Fuels reduction | Herbicide application | N/A | In progress | Shasta Valley RCD | 17850 | 0
1.2 | Scott Bar Ridge 1 | Private (industrial forestry) | 106 | Fuels reduction | Thinning | N/A | In progress | Shasta Valley RCD | 100700 | 0
1.3 | Scott Bar Ridge 1 | Private (industrial forestry) | 136 | Fuels reduction | Mastication | N/A | In progress | Shasta Valley RCD | 217600 | 0
1.4 | Scott Bar Ridge 1 | Private (industrial forestry) | 136 | Fuels reduction | Pruning | N/A | In progress | Shasta Valley RCD | 12920
1.5 | Scott Bar Ridge 1 | Private (industrial forestry) | 80 | Biomass_Utilization | Biomass removal | N/A | In progress | Shasta Valley RCD | 172000
2.1 | Scott Bar Ridge 2 | Private (industrial forestry) | 230 | Fuels reduction | Herbicide application | N/A | In progress | Shasta Valley RCD | 34500 | 0
2.2 | Scott Bar Ridge 2 | Private (industrial forestry) | 195 | Fuels reduction | Thinning | N/A | In progress | Shasta Valley RCD | 185250 | 0
2.3 | Scott Bar Ridge 2 | Private (industrial forestry) | 530 | Fuels reduction | Mastication | N/A | In progress | Shasta Valley RCD | 848000 | 0
2.4 | Scott Bar Ridge 2 | Private (industrial forestry) | 87 | Fuels reduction | Pruning | N/A | In progress | Shasta Valley RCD | 8265
2.5 | Scott Bar Ridge 2 | Private (industrial forestry) | 418 | Biomass_Utilization | Biomass removal | N/A | In progress | Shasta Valley RCD | 898700
3.1 | FGS Roadside Clearance | Private (industrial forestry) | 82 | Land protection | Mastication | N/A | N/A | Shasta Valley RCD | 0 | 121087
4.1 | MCTC Mill Creek 1 | Private (industrial forestry) | 375 | Fuels reduction | Herbicide application | N/A | In progress | Shasta Valley RCD | 56250 | 0
4.2 | MCTC Mill Creek 1 | Private (industrial forestry) | 46 | Fuels reduction | Thinning | N/A | In progress | Shasta Valley RCD | 43700 | 0
4.3 | MCTC Mill Creek 1 | Private (industrial forestry) | 242 | Fuels reduction | Mastication | N/A | In progress | Shasta Valley RCD | 387200 | 0
4.4 | MCTC Mill Creek 1 | Private (industrial forestry) | 242 | Fuels reduction | Pruning | N/A | In progress | Shasta Valley RCD | 22990
5.1 | MCTC Mill Creek 1 | Private (industrial forestry) | 227 | Biomass_Utilization | Biomass removal | N/A | In progress | Shasta Valley RCD | 488050 | 0
6.1 | MCTC Mill Creek 2 | Private (industrial forestry) | 106 | Fuels reduction | Herbicide application | N/A | In progress | Shasta Valley RCD | 15900 | 0
6.2 | MCTC Mill Creek 2 | Private (industrial forestry) | 61 | Fuels reduction | Thinning | N/A | In progress | Shasta Valley RCD | 57950 | 0
6.3 | MCTC Mill Creek 2 | Private (industrial forestry) | 49 | Fuels reduction | Mastication | N/A | In progress | Shasta Valley RCD | 78400 | 0
6.4 | MCTC Mill Creek 2 | Private (industrial forestry) | 49 | Fuels reduction | Pruning | N/A | In progress | Shasta Valley RCD | 4655
7.1 | MCTC Mill Creek 2 | Private (industrial forestry) | 29 | Biomass_Utilization | Biomass removal | N/A | In progress | Shasta Valley RCD | 62350 | 0
8.1 | KNF Fuel Reduction | USFS | 650 | Prescribed fire | Understory burn | Complete | N/A | Forest Service | 150000 | 400000
| All treated lands | Private (industrial forestry) | 1859 | Research | Research | N/A | N/A |  | 416942 | 52118
| All treated lands | Private (industrial forestry) | 1859 | Other | Other | N/A | N/A |  | 300000
Sums | -- | -- | 7913 | -- | -- | -- | -- | -- | 4580172 | 573205
Total acres treated in grant project: |  | 1859 | Count each acre only once even if it has multiple treatment activities applied.

## 3. Work Plan
CAL FIRE Tracking # 20-FH-SKU-010 Project Title: McKinley Scott Fuel Reduction |  |  |  | CAL FIRE Forest Health Program California Climate Investments (Required for all applicants: Forest Health, Research, and Forest Legacy.) | [7 empty] | Siskiyou County
Worksheet 3: Work Plan & Timeline
Applicant: Siskiyou County
Application ID:
For each treatment area or major task in this application, list the associated activities or phases of work and show timeline by quarter.
Activities associated with treatment implementation should be organized by treatment area. All treatment areas or other activities must be included.
See examples below. Add more rows if needed.
|  | 2021 | 2021 | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2026
Treatment Area or Major Task | Activity and/or Treatment Number | Jul-Sep | Oct-Dec | Jan-Mar | Apr-Jun | Jul-Sep | Oct-Dec | Jan-Mar | Apr-Jun | Jul-Sep | Oct-Dec | Jan-Mar | Apr-Jun | Jul-Sep | Oct-Dec | Jan-Mar | Apr-Jun | Jul-Sep | Oct-Dec | Jan-Mar
Scott Bar Ridge 1 | Herbicide application 1 | [11 empty] | X | X | X
| Thinning 2 | [8 empty] | X | X |  | X
| Mastication 3 | [8 empty] | X | X |  | X
| Pruning 4 | [8 empty] | X | X |  | X
| Biomass 5 | [7 empty] | X | X | X
Scott Bar Ridge 2 | Herbicide application 6 | [7 empty] | X | X | X |  | X
| Thinning 7 | [7 empty] | X | X | X |  | X | X | X
| Biomass10 | [7 empty] | X | X | X |  | X | X | X
| Mastication 6 | [7 empty] | X | X | X |  | X | X | X
| Pruning 9 | [7 empty] | X | X | X
AKF Roadside Clearance | Mastication 11 | [7 empty] | X | X | X |  | X | X | X | X
MCTC Mill Creek 1 | Herbicide application 12 | [9 empty] | X |  | X |  | X
| Biomass removal 13 | [7 empty] | X | X | X
| Mastication 14 | [7 empty] | X | X | X |  | X | X | X
| Pruning 15 | [7 empty] | X | X | X
| Thinning 16 | [6 empty] | X | X | X | X | X | X | X | X | X
MCTC Mill Creek 2 | Herbicide application 17 | [7 empty] | X |  | X |  | X |  | X
| Biomass removal 18 | [7 empty] | X | X | X |  | X | X | X | X
| Mastication 19 | [7 empty] | X | X | X |  | X | X | X
| Pruning 20 | [7 empty] | X | X | X
| Thinning 21 | [6 empty] | X | X | X | X | X | X | X | X | X
KNF Fuel Reduction 1 | Prescribed burning 22 | [6 empty] | X | X
KNF Fuel Reduction 2 | Prescribed burning 22 | [6 empty] | X | X
KNF Fuel Reduction 3 | Prescribed burning 22 | [10 empty] | X | X |  |  | X
KNF Fuel Reduction 4 | Prescribed burning 22 | [10 empty] | X | X |  |  | X
Wildlife Monitoring | 23 |  |  |  |  | X | X |  |  | X | X |  |  | X | X
Project effectiveness Monitoring | 24 |  |  | X | X | X | X |  | X | X | X |  | X | X | X | X

## 4. Environmental Compliance
CAL FIRE Tracking # 20-FH-SKU-010 Project Title: McKinley Scott Fuel Reduction |  | CAL FIRE Forest Health Program California Climate Investments (Forest Health: Required for all applicants. Research and Forest Legacy: Complete this worksheet only if treatments will be implemented using grant funds as a part of this project.) |  |  |  |  | Siskiyou County
Date:
Total funding for completing CEQA in CCI budget (if applicable): |  |  | 9000 |  |  |  | For SVRCD to act as Lead Agency
Environmental Documents Completed and Filed: Use this form for treatment activities covered by environmental documents that have been completed and filed with the State Clearinghouse.
Treatment Area | Treatment Type | Month, Year work will be completed | Lead Agency (federal) | Federal Envtl. Compliance Doc. | Lead Agency (state) | State Envtl. Compliance Doc. | Doc # | Date filed | Comment period ends
MCTC Mill Creek 1 | Biomass removal | 2022-05-01 | N/A | N/A | CAL FIRE | 1038.3 Forest Fire Prevention Exemption | 2-21EX-00693-SIS | 2021-05-12 | Ended
Craggy | Thinning, mastication, burning | 2024-12-30 | Klamath NF | EIS |  |  |  | 2018-05-22 | Ended
Straddler | Thinning, burning | 2024-12-30 | Klamath NF | CE |  |  |  | 2011-01-11 | Ended
McBaldy | Thinning, mastication, burning | 2024-12-30 | Klamath NF | EA |  |  |  | 2009-08-20 | Ended
Singleton | Thinning, mastication, burning | 2024-12-30 | Klamath NF | EA |  |  |  | 2012-07-05 | ended
Scott Bar Mtn | Underburning, fuel break | 2024-12-30 | Klamath NF | CE |  |  |  | 2015-04-17 | ended
Notes:
Environmental Documents Not Completed: Use this form for treatment activities for which environmental documents have NOT been completed.
Treatment Area | Treatment Type | Month, Year work will be completed | Lead Agency (federal) | Federal Document Being Prepared | Lead Agency (state) | State Document Being Prepared | Contractor completing documentation | Completion timeline
Scott Bar and Mill Creek properties | McKinley Scott Fuel Reduction Project | 2023-03-15 | N/A | N/A | Shasta Valley RCD | Environmental Review Report for an Exempt Project | FWS RPF | 2023-03-15
Notes:

## Menus
OwnershipType | Objectives | Fuels_Reduction | Prescribed_Fire | Pest_Management | Reforestation | Biomass_Utilization | Research | Forest_Conservation | Other | NEPA/CEQA Status
BLM | Fuels_Reduction | Chipping | Broadcast Burning | Chipping | Fencing | Biomass Removal (Biochar) | Demonstration | Facilitated Donation | Other | Completed
BLM (wilderness) | Prescribed_Fire | Commercial Thinning (Tractor Yarding) | Cultural Burning | Crushing | Herbicide | Biomass Removal (Electricity) | Data Collection | Purchase Fee Title |  | In Progress
National Park | Pest_Management | Commercial Thinning (Cable Yarding) | Pile Burning | Fungicide | Invasive Plant Removal | Biomass Removal (Heat) | Imagery Data Collection | Purchase Conservation Easement |  | N/A
National Park (wilderness) | Reforestation | Fuel Break (Shaded) | Oak Woodland Restoration | Herbicide | Oak Woodland Restoration | Biomass Removal (Renewable Fuels) | Research | Other
Department of Defense | Biomass_Utilization | Fuel Break (Not Shaded) | Site Preparation | Insecticide | Road Removal | Biomass Removal (Wood Products) | Data Collection
Forest Service | Research | Grazing | Other | Invasive Plant Removal | Site Preparation | Piling (Manual) | Other
Forest Service (wilderness) | Forest_Conservation | Herbicide |  | Piling (Manual) | Tree Planting (Manual) | Piling (Mechanical)
Other Federal | Other | Invasive Plant Removal |  | Piling (Mechanical) | Tree Planting (Mechanical) | Other
State Demonstration Forest |  | Lop and Scatter |  | Pile Burning | Tree Shelters
State Park |  | Mastication |  | Pruning | Other
Other State |  | Piling (Manual) |  | Removal of Diseased/Infested Trees
Local Government |  | Piling (Mechanical) |  | Tarping
Special District |  | Pile Burning |  | Thinning (Manual)
Tribal |  | Pruning |  | Thinning (Mechanical)
Private (industrial forestry) |  | Oak Woodland Restoration |  | Other
Private (non-industrial) |  | Right of Way Clearance
Other |  | Thinning (Manual)
Thinning (Mechanical)
Other