## 26-27
SISKIYOU COUNTY SB-1 2026/27
ROAD MAINTENANCE AND REHABILITAION (RMRA) PROJECT LIST
[7 empty] | ATTACHMENT "A" |  |  | 2026/27 RMRA | 6190090
Work | Road | Project |  |  | Road | Est. Useful | Mile Post | Mile Post |  |  | Completion | CAMS Project Number
Order Num | Dist. | Title | Project Description | Road Name / Location | Number | Life (Years) | Begin | End | Length | Estimate | Date Est.
SB-1 Routine Maintenance Project List
| All | Roadway Striping and Pavement Markings. - Countywide- | This routine maintenance item includes restriping Centerline, edge line and reapplying painted and thermoplastic legends stop bars and crosswalks Countywide. | Various locations throughout Siskiyou County that currently have existing paint or thermoplastic pavement markings. Areas include Mt Shasta, Montague, Scott valley, Dorris, Tulelake, Happy camp, Gazelle, and Yreka. |  | 1-2 | N/A | N/A |  | 300000 | 2026-06-30 | 2103-RD 2627 STRIP
| All | Sign upgrade and Maintenance - Countywide- | This project includes procurement of sign materials, upgrading of Regulatory signs to meet the Retroreflecivity requirement. Project will also include maintenance of road side delineation and post repair. | Location will be determined by priority based on routine Retroreflecivity Study. Locations subject to change based upon needs and available resources throughout the year. |  | 5-7 | N/A | N/A |  | 150000 | 2027-06-30 | 2103-RD 2627 SIGNS
| All | Roadside Tree Trimming and Vegetation Management | This project consists of hazard tree removal, tree trimming, mowing and road side grass and weed control. Countywide. | Various location throughout Siskiyou County based on need. Planed areas include Klamath River Rd, McCloud area and the Mt Shasta area, Yreka and Montague area, Scott Valley area. |  | 1-2 | N/A | N/A |  | 500000 | 2027-06-30 | 2103-RD 2627 VEG MGT
| All | Gravel Road Maintenance | This routine maintenance item includes gravel grading and surface application of crushed rock. | Various location Countywide. Roads include but are not limited to: Louie Road, Old State Hwy, Sheepy Creek Road, Dorris Brownell Road, Willow Creek Red Rock Road, Big Springs Road, York Road, Willow Creek Road, Crushed rock application will be prioritized by need. |  | 1-5 | N/A | N/A |  | 800000 | 2027-06-30 | 2103-RD 2627 GRVL RDS
| All | Aggregate Production/Purchase | This project will consist of production of aggregate materials at the County's Yellow Butte, Little Lynn, and aggregate purchases for Districts 4,5 and 6. | Yellow Butte cinder production and other aggregate purchases. Little Lynn Pit crushing contract. |  | 1-3 | N/A | N/A |  | 361046.28 | 2027-06-30 | 2103-RD 2627 AGG PROD
| All | Maintenance/Rehabilitation of existing unpaved shoulder | This routine maintenance item will consist of re-profiling, grading and adding aggregate base material were needed. | This will be a Countywide project. Shoulder improvements will be prioritized by current condition. Areas include Montague Yreka, Gazelle, Scott Valley, Dorris, and Mt Shasta. |  | 1-2 | N/A | N/A |  | 350000 | 2027-06-30 | 2103-RD 2627 SHOULDER
| All | Culvert and Ditch Maintenance | This project will consist of debris removal from drainages, ditches and culverts, reestablishing ditch lines. In an effort to maintain flow lines and reduce the potential for flooding and sediment disbursement into waterways. | Various location throughout Siskiyou County based on need. Planed areas include Mt Shasta area, Montague area,Gazelle area,Scott valley area, Butte valley area and the Happy Camp area. |  | 1-3 | N/A | N/A |  | 600000 | 2027-06-30 | 2103-RD 2627 DITCH
| All | Pavement patching | Project consists of pothole repair, thin asphalt overlay, crack fill and sealing, with the intent of repairing unsafe, damaged or failing roadway. | This is a Countywide project. Priority will be dictated by need and roadway safety. Areas include Yreka, Montague, Scott Valley, Mt Shasta, Gazelle, Dorris, Happy Camp, and Tulelake. |  | 1-5 | N/A | N/A |  | 800000 | 2027-06-30 | 2103-RD 2627 PACTH
| All | Maintenance of Public Works Equipment. | Project consists of repair and servicing of Public Works equipment. | Located at all facilities; Cental Shop Yreka, Gazelle Shop, Mt Shata Shop, Etna Shop, Fort Jones Shop, Dorris Shop, Happy Camp Shop, Forks Salmon Shop. |  | 1-2 | N/A | N/A |  | 800000 | 2027-06-30 | 2103-RD 2627 EQUIP MT
[7 empty] | Routine Maintenance Total |  |  | 4661046.28
[7 empty] | 20/21 RMRA Allocation |  |  | 4192019
[7 empty] | Total left for Rehab Projects |  |  | -469027.28
[7 empty] | Per District Project Allocation |  |  | -78171.2133
SB-1 Preventative Maintenance Project List
| 1 | Chip Seal District 1 | Project consists of asphalt repair with follow-up 3/8" chip seal. | Harry Cash. | 7L01 | 5-7 | MP 0 | MP, 4 | 4 | 263195.51 | 2027-09-30 | 2103-RD RMRA 2627 A
| 2 | Chip Seal District 2 | Project consists of asphalt leveling course. | W.A Barr Rd. | 2m22 | 5-7 | MP 0 | MP, 1.4 | 1.4 | 250780.45 | 2027-09-30 | 2103-RD RMRA 2627 B
| 3 | Chip Seal District 3 | Project consists of asphalt leveling course. | Siskiyou Ave. | 6K02 | 5-7 | MP 1.85 | MP, 3 | 1.15 | 231033.86 | 2027-09-30 | 2103-RD RMRA 2627 C
| 4 | Chip Seal District 4 | Project consists of asphalt repair with follow-up 3/8" chip seal. | Oro Fino Rd, Lighthill Rd. | 5G025, 4G04 | 5-7 | MP 3.23, MP 5.78 | MP 1.63 MP 5.04 | 1.6, 0.74 | 307572.11 | 2027-09-30 | 2103-RD RMRA 2627 D
| 5 | Chip Seal District 5 | Project consists of asphalt repair with follow-up 3/8" chip seal. | East Callahan Rd, Fay Lane | 4G008, 3G006 | 5-7 | MP 0, MP 0 | MP 3.01, MP 0.98 | 3.99 | 247379.57 | 2027-09-30 | 2103-RD RMRA 2627 E
| 6 | Chip Seal District 6 | Project consists of asphalt leveling course. | Meiss Lake Sams Neck Road. | 8Q020 | 5-7 | MP 0 | MP 3.6 | 1.5 | 229082.22 | 2027-09-30 | 2103-RD RMRA 2627 F
[7 empty] | Rehab Project Total |  |  | 1529043.72
[7 empty] | SB-1 RMRA PROJECT ESTIMATE TOTAL |  |  |  | 6190090
Note on L4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We do recommend providing state and completion dates, since that is the information required when entering it into CalSMART
Note on D16: Todd Lamanna: Including Autoserve costs